## Sheet1
Sl. no. | File Path | Comments | Dev. Name | Dev. Status | QA Status
1 | manager/greeting-setup.php |  | Mahendra | Done | 1.On clicking edit icon, the user is shown URL : https://app.sppreprod.ingreeting-setup.php/?tab=quick-action&edit=SkRNMU1TRTlVR0JnQ21BSw== 2.On clicking the delete icon, the user is shown URL : https://app.sppreprod.ingreeting-setup.php/?tab=quick-action&delete=SkRNMU1VcytZR0JnQ21BSw== Confirmation needed from PM : 3.After changing the order of the icons from the admin panel, the changes are not reflected in the mobile app until the user logs out and logs in again. | Done
2 | manager/sp-microsite-setup.php |  | Mahendra | Done | 1.On clicking Remove button and then saving it, the user is shown older image only. This should not happen, the user should be shown default image. | Done
3 | manager/apis/V2/sp-digi-card.php |  | Mahendra | Done | After adding a photo in the Digicard, the photo is reflected in 10-15 seconds. The APIs response is quite slow. | Done
4 | manager/apis/V2/appUserDetails.php |  | Mahendra | Done | Done
5 | framework/api/appUserDetails |  | Mahendra | Done | Done
6 | manager/apis/V2/sp-mobileappprofile.php |  | Mahendra | Done | Done
7 | manager/apis/V2/sp-mobileapp-updateprofile.php |  | Mahendra | Done | Done
8 | home/AssetLibrary |  | Mahendra | Done | Done
9 | framework/api/authenticate |  | Mahendra | Done | Will Done Together
10 | framework/api/spssologin |  | Mahendra | Done | Will Done Together
11 | mahendraraj.sppreprod.in/website/ |  | Mahendra | Done
12 | mahendraraj.sppreprod.in/site/ |  | Mahendra | Done
13 | manager/landingpage-dashboard.php | Create, Edit, Access | Mahendra | Done | Done
14 | manager/contact.php | list, create, edit, delete | Mahendra | Done | 1.While adding a contact to a list. The user is shown : This page isn’t working app.sppreprod.in is currently unable to handle this request. HTTP ERROR 500 2.When the user clicks on the Send Email button, the user is shown : This page isn’t working app.sppreprod.in is currently unable to handle this request. HTTP ERROR 500 3.Uploading Contacts through CSV not working. Even after uploading successfully, still the contacts were not shown neither Email received to the user. | Done
15 | manager/cta.php |  | Mahendra | Done | Done | Done
16 | manager/sp-document-list.php |  | Mahendra | Done | 1.Notification not received to the users when the Admin directly syndicated(With/Without Schedule) the content. 2.Even after marking the content as downloadable, still it does not show as Downloadable in the mobile app (Happened for With/Without Schedule content). 3.Images are broken of older Documents shown in the listing. | Done
17 | /manager/setup.php |  | Mahendra | Done | 1.Not Able to connect any of the Social medias from the child's web account. | Done
18 | Journey |  | Mahendra | Done
19 | CHLIHeirarchy |  | Mahendra | Done
20 | LeadStage |  | Mahendra | Done |  | Done
21 | Calculators |  | Mahendra | Done
22 | new-add-lead-proces_for_chatbot.php |  | Mahendra | Done |  | Done
23 | framework/banners | list, create, edit, delete | Mahendra | Done |  | Done
25 | manager/front-end-design.php |  |  | Done
26 | manager/send-campign-process.php |  |  | Done
27 | manager\add_enablement_courses.php |  |  | Done
28 | manager\add_visa_campaign.php |  |  | Done
29 | manager\course-preview.php |  |  | Done
30 | manager\courses_list.php
31 | manager\excel_upload_incentiveclub.php
32 | manager\excel_upload_incentivecontest.php
33 | manager\incentive-club-dashboard.php
34 | manager\incentive-contest-dashboard.php
35 | manager\incentive-contest-map-excel.php
36 | manager\incentive-file-upload.php
37 | manager\incentive-target-dashboard.php
38 | manager\master_campaign_list.php
39 | manager\attachment-upload.php
40 | manager\create-text-template.php
41 | manager\edit-template-content_new.php
42 | manager\edit-upload-file.php
43 | manager\google-manage.php
44 | manager\new-chatbot.php
45 | manager\prospect-activity.php
46 | manager\sp-achievements-list.php
47 | manager\sp-commcreate.php
48 | manager\sp-communication.php
49 | manager\sp-editbanner-creative.php
50 | manager\sp-editcommcreate.php
51 | manager\sp-editcommcreateV2.php
52 | manager\sp-hdfcdoc-list.php
53 | manager\sp-internal-document-list.php
54 | manager\sp-manage-testimonials.php
55 | manager\sp-micrositetemplate-list.php
56 | manager\sp-successfull-list.php
57 | manager\sp-testimonials-list.php
58 | manager\sp-unsuccessfull-list.php
59 | manager\sp-upload-customdocument.php
60 | manager\sp-upload-document.php
61 | manager\text-template-list.php
62 | framework\resources\views\calculator\create.blade.php
63 | manager\apis\V2\appCampaignIndividualDashboard.php
64 | manager\add_new_email.php
65 | manager\category-edit.php
66 | manager\chatbot-setup.php
67 | manager\edit_email.php
68 | manager\eng-window-individual-analytics.php
69 | manager\greeting-setup.php
70 | manager\hashtag-image-solution.php
71 | manager\hashtag-solution.php
72 | manager\insert-upload-edm-template.php
73 | manager\lead-scope.php
74 | manager\main_campaigns.php |  |  |  | Done
76 | manager\showcase-analytics-individual-dashboard.php
77 | manager\sp-listsearch.php
78 | manager\sub-category-edit.php
79 | manager\tasks-list.php
80 | Email Campaign PHP (Direct,Auto-Email) |  |  |  | 1.Not able to add a link before sending the campaign. Every email we send, it has an option of adding a link in one of the Buttons in the HTML. | Done
81 | Email Campaign PHP (Direct) - CHILD ACCOUNT |  |  |  | 1.The Child User is not able to add a personalize variable. 2.Not able to send Campaign without Schedule. The User stays on the same screen. URL : https://app.sppreprod.in/manager/runcampaign.php?action=campaign&camp_id=S0RNMU1TRXNWRlZLTlROVVlBcGdDZz09&lpage_id= 3.Email Scheduled from Child Account remained in Scheduled only. 20/05/2026 4.When the user edits the contact list and adds a new contact, they are all the fields blank. (JIRA WILL BE MADE) | Done
82 | Document Library (LARAVEL - framework/DocumentLibrary/list) |  |  |  | 1.Images are broken of older Documents shown in the listing. | Done
83 | General Setup > Facebook Page,LinkedIn,Twitter (URL : framework/general-setup/social-list) General Setup > Contact Limit General Setup > Branding |  |  |  | 1.Not able to connect Twitter and Google Business. 2.Image is broken under the Banner section of Branding. | Done
84 | Testimonials (Child Account) |  |  |  | 1.If the User adds a Testimonial without image, then a broken image is shown. | Done
85 | Achievements (Child Account) |  |  |  | Done
86 | Cadence |  |  |  | 1.After saving a Task inside an Activity. When the Admin clicks on that Task again, they are just shown the description of the Task but no Title. | Done
87 | Asset Library > Banners |  |  |  | Done
88 | Asset Library > Email Template (REACT) |  |  |  | 1.Template made for Indirect Campaign are shown in the Direct Campaign as well. | Issue on prod server
89 | App Banners (framework/banners) |  |  |  | 1.While editing an existing Banner (Banners without Link), not able to save them.
90 | Social Auto Post |  |  |  | Vaishali is fixing bugs.
91 | Conversion > CTA (manager/cta.php) |  |  |  | Done
92 | Conversion > Calculators (framework/calculatorslist)
93 | Conversion > Proposals |  |  |  | 1.Need to confirm from Harish Sir. As no Calculator was being shown when viewed it on web after creation.
94 | Pipeline (Admin) > Leads (manager/lead.php) |  |  |  | 1.While searching, the user is shown Something went wrong message. 2.When we select a contact, click on send email and then select the template, the To textfield is shown empty. 3.While sending an email to contact, the Admin is not able to do so and a message is being shown "Email has not been sent". And one more message is shown Invalid email detected: 172726167686176766f6872613230313440676d61696c2e636f6d723c3c53505f425a3e3e726167686176766f6872613230313440676d61696c2e636f6d. 4.Not able to send Test Email. | Done
95 | Pipeline (Admin) > Partner Leads (manager/lead.php) |  |  |  | 1.Uploaded Partner Leads CSV, but Leads were not reflected in the listing. I checked it after 15 minutes. | Done
96 | Microsite PHP |  |  |  | 1.Chatbot : Answer all questions and then select the category, then click on any pdf content in it, the user is shown broken images. 2.Notifications not received from Lead filled from chatbot. 3.Category > Pdf Content : Click on any pdf of any category, most of the pdfs have broken images.
97 | Microsite (Website) |  |  |  | Need to confirm whether we can test this microsite on Preprod.
98 | Asset Library (Image,Video,Stories,Pdf) |  |  |  | 1.On sharing Story through Other option, the user is shown "File not Found". | Issue on prod server
99 | Mobile App |  |  |  | 1.The App throws something went wrong message whatever action we perform. Clicking on the Content Notification Alert, on redirection we are first shown Something Went Wrong message. 2.On sharing Video,Story through whatsapp, the user is shown infinite loader. | Done
100 | Courses |  |  |  | 1.When we change the order from the right side (Order Quiz Questions), new questions got added. 2.When the User clicks on "Next" button till last, the screen becomes small. 3.When we add an audio and then open it in the mobile, we are shown "Start Quiz". 4.When the User clicks on the Get Certificate button on a course, the user is not able to click on View,Download,Share in the mobile app. 5.Certificate tab shows broken image. 6.Search is not working in the Partner tab. And when we click on it, it shows "Processing". 7.After making the Course with Quiz, then again editing the course by adding a quiz question, the user is shown "Quiz updated successfully" after first click but the question is not shown in the Order Quiz Questions section. When the user clicks for the second time on save button, user is shown Quiz Question Required. 8.When the user has added all the questions in the quiz, but has forgot to enter the percentage. Then updates the percentage, the user is shown "Please add Quiz Question". 9.Special character issue in the Course > Lesson name. 10.When the user adds questions in the quiz then adds percentage, then saves. Then again comes back and edits the percentage is no more shown.